# 7th FIELDS WP1 meeting

**Subject:** ongoing tasks

**Participants:** several WP1 task leaders

**Date:** 21 July 2020, 14:30-15:30

**Topics discussed**

* Luis Mayor (ISEKI) suggests that deliverable checking be done just for 2 members of the HSC. Francesca Sanna (UNITO, project manager) says that better wait and see how works the procedure for following deliverables, since we have had tight schedules and that’s why few people has checked them. Hopefully it will work better in the future.
* Best practices database has few inputs. In the next meeting we will see if number of inputs have increased, otherwise we will ask partners to enrich the database.
* Deliverable 1.1: let us try to have a meeting to advance with the deliverable. Some info has been collected from partners and UNITO will start to work on it, with the collaboration of WUR, CONFAGRI and UHOH. Maria Joao Proença (EfVET), as requested in the project description, has prepared a report on educational frameworks (ECVET, EQAVET, ESCO, EQF) describing how they work and some basic considerations to use them in our project. It will be included in D 1.1. The project description includes enough references on how to link these frameworks with the project, so it is not necessary this information.
* LM indicates that ISEKI is working on the FG analysis at national level, although some data have still to be sent to ISEKI (deadline is end of July).
* Next meeting, date to be decided in September.