## Slide 1: Setup and running of Train the Trainer Session WP 4.1
Taskleader:
AGRAR Plus (AP)
Participating organisations:
UNITO, CONFAGRI, ISEKI, AERES,UHOH,ICOS, ACTIA, CERTH, GAIA, CONFAGRI,PT, GZS, LVA, UCLM, AC3A, INFOR, EFB, PA, CEPI

## Slide 2: Setup and running of Train the Trainer Session
Duration (M26 – 36)
Selection of trainers (M24 – 27)
  Suggestion: according to focus group results (lack of knowledge and skills)
Material and monitoring tools have to be ready to use before Train the Trainer Session (TtTS)
As preparation for TtTS, selected Trainers get familiar with online content over a period of two weeks
  Content providers (INFOR, EFB, UCLM, UNITO, AP, CERTH, PA) give support
Feedback to content for modifications on content and roadmap per country T2.4
  Satisfaction survey prepared, collected and evaluated by AP  D4.1 Feedbacks from Trainers
Training material for trainers on open source Learning management system chosen in T3.1

## Slide 3: Setup and running of Train the Trainer Session
practical things:
Duration: 3 days inclass training
Venue: Sankt Poelten, Austria
Date: depending on Material/Platform availability
Training on expenses of AGRAR Plus
Each stakeholder representative of Agriculture, Forestry, Bioeconomy and VET Center (AC3A, ACTIA, AERES, AP, CEPI, CONFAGRI, CONFAGRI PT, UHOH, EFB, GAIA, ICOS, INFOR, LVA, PA, SCOOP, UCLM, UNITO) provides one trainer and cover its expenses for TtTS