## Slide 1: WP5 – Long term action plan
Lifelong Learning Platform
Erika Somlyay, erika.somlyay@lllplatform.eu
TPM Paris
30-31/05/2022

## Slide 2: WP5 – T5.2 Funding opportunities
WP Start/end date: M7-M24 (completed)
Partners involved: CONFAGRI, WUR, ICOS, AERES, AP, UHOH, CERTH, ACTIA, GAIA, AC3A, CONFAGRI PT, GZS, LVA, FIAB, FDE, INFOR, SEVT, EFVET, CEPI
Main Objectives:
List the funding opportunities available to support the skills strategies and the future use of FIELDS’ outputs.
Funding levels: (regional/national and EU levels).
Main targets: i) fundings to put into practice the strategy (implementation of training based on the developed curricula, policy making, etc) and ii) fundings to maintain and ensure the future use of the project outputs (platform maintenance and update).

## Slide 3: WP5 – T5.2 Funding opportunities
Task implementation
The criteria for selecting the funding opportunities were determined by LLLP after receiving feedback from partners. The funding opportunities must:
Be in the European Union
Be relevant to the projects in terms of:
  Dealing with one or several topics: digitalisation, agriculture, forestry, (soft) skills, business/entrepreneurship, sustainability.
  Partners to be eligible to apply for them
The funding opportunities database, which was overseen by UNITO, consists a table that includes thirteen columns for collecting basic information related to each specific funding opportunity.

## Slide 4: WP5 – T5.2 Funding opportunities
Task Results (see report)
Project themes: most prominent digitalisation and less prominent bioeconomy.
Funding: most prominent national level and level of funding under the 100,000 euros funding mark.
Beneficiaries: the funding opportunities which target both private and public organisations had the biggest proportion.
Partners feedback:
  Funding programmes: EU level funding programmes among which Erasmus+ is the most popular option.
  New applications: involving FIELDS partners for joint applications, joint applications would be better suited for some of them and they are open to applying with partners if invited to suitable calls.
  Objectives and topics: exchanging good practises, improving training methodologies, climate change mitigation, waste prevention, food safety, and technology developments.

## Slide 5: WP5 – T5.2 Funding opportunities
Task conclusions, recommendations and next steps
There is a wide range of funding opportunities for project partners covering the different project themes and at different levels (EU, National and Regional).
The database will be a helpful tool for the sustainability of the project but to be successful it needs to remain useful to partners. NEW CALL FOR UPDATES - FALL 2022
This also means that the database can be useful for current and future project tasks/activities.
  WP 3 and WP 4: to connect the work they are doing with potential opportunities to further develop their deliverables.
It is also recommended to provide opportunities for partners to share their new project ideas during FIELDS work package or task meetings and/or coordinate specific project brainstorming meetings.